## API Estimation Detail
API Development Time Estimation · Scope of Work
Stack: Python · FastAPI · Microsoft Graph API · Unifonic SMS · JWT · OAuth 2.0 / OIDC
PERT Estimate = (Best + 4 × Likely + Worst) / 6 ¦ Days = PERT Hours ÷ 8
# | Module | API / Task | HTTP Method | Best (hrs) | Likely (hrs) | Worst (hrs) | PERT Est (hrs) | Days (8h) | Complexity | Notes / Dependencies
1. USER REGISTRATION APIs
1 | User Registration | Register via Email | POST | 2 | 4 | 6 |  |  | Medium | Validate email format, check duplicate, hash password, generate verification token
2 | User Registration | Register via Mobile Number | POST | 2 | 4 | 6 |  |  | Medium | E.164 format validation, duplicate check, trigger OTP via Unifonic
3 | User Registration | Verify OTP – Registration | POST | 1 | 2 | 4 |  |  | Low | Validate OTP code, expiry check, mark account active
4 | User Registration | Resend OTP | POST | 1 | 2 | 3 |  |  | Low | Rate-limit resend attempts, regenerate token, re-trigger Unifonic
2. UNIFONIC SMS INTEGRATION
5 | Unifonic SMS | Send OTP – Registration | POST | 2 | 3 | 5 |  |  | Medium | Unifonic REST API wrapper; template management, retry on failure
6 | Unifonic SMS | Send OTP – Login | POST | 1 | 2 | 3 |  |  | Low | Reuse Unifonic service; login-specific template
7 | Unifonic SMS | Send OTP – Password Reset | POST | 1 | 2 | 3 |  |  | Low | Password reset template; link expiry in message body
8 | Unifonic SMS | OTP Validation & Expiry Mgmt | – | 2 | 4 | 6 |  |  | Medium | Time-based OTP validity (5 min), single-use enforcement, Redis/DB store
3. MICROSOFT GRAPH API INTEGRATION
9 | MS Graph API | Create User in Entra External ID | POST | 3 | 5 | 8 |  |  | High | Graph API auth (client credentials), map registration payload to Entra schema
10 | MS Graph API | Update User Profile in Entra | PATCH | 2 | 4 | 6 |  |  | Medium | Delta update only changed attributes; handle Entra rate limits
11 | MS Graph API | Retrieve User Information | GET | 1 | 3 | 5 |  |  | Medium | Fetch by objectId or email; map Entra attributes to local model
12 | MS Graph API | Manage Custom User Attributes | PATCH | 3 | 5 | 8 |  |  | High | Define extension attributes in Entra; read/write via Graph extensions endpoint
13 | MS Graph API | Graph API Auth Module (service) | – | 3 | 5 | 7 |  |  | High | OAuth 2.0 client_credentials flow; token cache; refresh logic; unit tests
4. PROFILE MANAGEMENT APIs
14 | Profile Mgmt | View Profile | GET | 1 | 2 | 3 |  |  | Low | Return profile from local DB + Entra merge; mask sensitive fields
15 | Profile Mgmt | Update Profile | PATCH | 2 | 4 | 6 |  |  | Medium | Validate fields (DOB, mobile format, country code), sync to Entra via Graph
5. USER MIGRATION
16 | User Migration | CSV Ingestion & Validation Script | – | 3 | 5 | 8 |  |  | High | pandas-based reader; schema validation; duplicate detection; error report CSV
17 | User Migration | Data Transformation Layer | – | 2 | 4 | 6 |  |  | Medium | Map CSV columns to Entra schema; handle nulls, encoding, phone normalisation
18 | User Migration | Bulk User Creation via Graph API | POST | 4 | 6 | 10 |  |  | High | Batch Graph calls (≤20/req); throttle handling; idempotency; progress log
19 | User Migration | Password Reset / Temp Password | POST | 2 | 3 | 5 |  |  | Medium | Assign temp password; force-reset flag in Entra; trigger welcome SMS/email
20 | User Migration | Migration Error Handling & Retry | – | 2 | 4 | 6 |  |  | Medium | Retry queue for failed records; partial success report; audit trail
6. AUTHENTICATION & SECURITY
21 | Auth & Security | Login – Email + Password | POST | 2 | 4 | 6 |  |  | Medium | Verify credentials, issue JWT (access + refresh tokens), log event
22 | Auth & Security | Login – Mobile OTP | POST | 2 | 3 | 5 |  |  | Medium | Trigger Unifonic OTP; validate; issue JWT on success
23 | Auth & Security | Password Reset – Request OTP | POST | 1 | 2 | 4 |  |  | Low | Lookup account by email/mobile; trigger Unifonic reset OTP
24 | Auth & Security | Password Reset – Set New Password | POST | 2 | 3 | 5 |  |  | Medium | Validate OTP, enforce password policy, update in Entra + local DB
25 | Auth & Security | Token Refresh | POST | 1 | 2 | 3 |  |  | Low | Validate refresh token, rotate & issue new pair, revoke old
26 | Auth & Security | Logout / Token Revocation | POST | 1 | 2 | 3 |  |  | Low | Blacklist token in Redis/DB; clear session state
27 | Auth & Security | JWT Middleware (FastAPI Dependency) | – | 2 | 4 | 6 |  |  | Medium | Decode & verify JWT on every protected route; role/scope extraction
28 | Auth & Security | Error Handling & Logging Infra | – | 2 | 4 | 6 |  |  | Medium | Structured logging (JSON), error codes, Sentry/CloudWatch hook, stack traces
7. CROSS-CUTTING & INFRASTRUCTURE
29 | Infrastructure | FastAPI Project Scaffold & Config | – | 2 | 4 | 6 |  |  | Medium | Project structure, .env config, DB connection pool, CORS, docs (OpenAPI)
30 | Infrastructure | Database Schema & Migrations | – | 2 | 4 | 6 |  |  | Medium | SQLAlchemy models / Alembic migrations for users, OTP, audit tables
31 | Infrastructure | Unit & Integration Test Suite | – | 4 | 8 | 12 |  |  | High | pytest + httpx; mock Graph API & Unifonic; ≥80% coverage target
32 | Infrastructure | API Documentation (OpenAPI/Swagger) | – | 1 | 2 | 3 |  |  | Low | Auto-generated via FastAPI; manual descriptions for all endpoints
33 | Infrastructure | Deployment Config (Docker / CI) | – | 2 | 4 | 6 |  |  | Medium | Dockerfile, docker-compose, GitHub Actions CI pipeline, env secrets
TOTAL (33 APIs / Tasks) | [9 empty] | See Summary sheet for phase breakdown

## Project Summary
Project Summary & Effort Breakdown
Estimates use PERT method (3-point): Best / Likely / Worst · 1 day = 8 hrs · 1 sprint = 10 days
# | Module / Phase | APIs Count | Est Hours (PERT) | Days (÷8) | Sprints (÷10) | Key Deliverables
1 | User Registration APIs | 4 | 44 |  |  | Register (Email+Mobile), OTP verify, Resend OTP
2 | Unifonic SMS Integration | 4 | 44 |  |  | OTP send wrappers, validation, expiry management
3 | Microsoft Graph API Integration | 5 | 72 |  |  | User CRUD in Entra, custom attributes, auth module
4 | Profile Management APIs | 2 | 22 |  |  | View + Update profile, Entra sync
5 | User Migration | 5 | 76 |  |  | CSV ingest, transform, bulk create, password reset
6 | Authentication & Security | 8 | 82 |  |  | Login flows, JWT, OTP reset, middleware, logging
7 | Cross-cutting & Infrastructure | 5 | 66 |  |  | Scaffold, DB schema, tests, docs, Docker/CI
GRAND TOTAL (33 APIs / Tasks)
DELIVERY ASSUMPTIONS & TIMELINE PARAMETERS
COMPLEXITY & RISK LEGEND
Low |  | Simple CRUD, single service call, minimal validation
Medium |  | 2+ service dependencies, async, validation logic
High |  | External API + auth flow, batch processing, migrations, test coverage required